## Gantt Chart
GANTT CHART TEMPLATE: GROUP 2.
PROJECT TITLE: |  | Class View ID |  |  |  |  | GROUP NAME's: |  | George McFarlane, Anthony Kotopoulos, Aden Mustafa, Thomas Damcevski
[7 empty] | START DATE - END DATE: |  | 24/07/25 - TBF
AREA NUMBER | TASK TITLE | TASK COMPLETER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | SECTION ONE |  |  |  | SECTION TWO |  |  | SECTION THREE |  |  | SECTION FOUR
[7 empty] | HOUR 1 | HOUR 2 |  | HOUR 3 | HOUR 4 | HOUR 5 | HOUR 6 | HOUR 7 | HOUR 8 | HOUR 9 | HOUR 10 | - | -
1 | Project Conception and Planning
1.1 | Idea Generation | GROUP | 2025-07-24 | 2025-07-25 | 1 | 100%
| Creating the Gantt Chart | ADEN | 2025-07-24 | 2025-07-25 | 2 | 0%
| Begin Logbook (Post to Repository) | GEORGE | 2025-07-24 |  | 10 | 0%
| Project Propsal Form | THOMAS | 2025-07-24 | 2025-07-25 | 1 | 100%
2 | Research and Development Stages
| Research Features of Project | ADEN | 2025-07-25 |  | 2025-03-02 | 0%
| Create Surveys to Gather Research | ANTHONY |  |  | 2 | 0%
| Plan Limits and Features |  |  |  |  | 0%
| Make Non-functional Requirments |  |  |  |  | 0%
| Consider Constraints of Idea |  |  |  |  | 0%
| Finalize Which Features are Being Used |  |  |  |  | 0%
| Create Possible Pseudo Code |  |  |  |  | 0%
| Create Possible Designs |  |  |  |  | 0%
| Make Criteria or What is Needed in designs |  |  |  |  | 0%
3 | Revison and Development Stages Continued
| Decide on Product Delivery Format (Look at Page 51 for Example) | GROUP |  |  |  | 0%
| Creating Blue prints for the invention. | THOMAS |  |  |  | 0%
| Rename the Project | GROUP |  |  |  | 0%
4 | Testing and Evaluation
| See if Idea is Efficent |  |  |  |  | 0%
| Montier Possible Oversights |  |  |  |  | 0%
5 | Final Revisons
| Finish Logbook |  |  |  |  | 0%
| Finalize the Project |  |  |  |  | 0%